Review of Milestone Draft Above :

PRO ENGINEERING — MILESTONE SUB-STAGE STRUCTURE

LAYER 1 — THE FIVE MAIN STAGES (Fixed for any Turnkey Job)

Every turnkey job design starts with 5 milestone stages. Fixed at co-ordinator. If co-ordinator wants he can send to Admin for approval. Co-ordinator or Admin can add milestones if needed. Estimate generated provides for each mile stone : description , number of skilled and unskilled category needed each day ( even in hours and timing slot as there may be limited work scope that day or activity is small), number of days or time in any day when any Milestone is reached, work done till mile stone, billing cost ( different for staff only / material only / turn key ) , reporting form with items ( including items of quality tick/ rework required/ rectification required if any ) and tap response on this items( photo and video (if required)). Supervisor has to check the reporting form and prescribe what percentage of milestone shall be payable staff and as perprotocol of bill amount say 1 lac or more the assigned role person to pass.

Create the structure to fill these values by co-ordinator.

Stage 1 — Mobilisation & Preparatory Works    (M0) — 20% of total

Stage 2 — First Fix (Civil + MEP Rough-in)    (M1) — 25% of total

Stage 3 — Mid Works (Waterproofing + Screed)  (M2) — 20% of total

Stage 4 — Second Fix (Finishing + Tiling)     (M3) — 25% of total

Stage 5 — Handover & DLP Start                (M4) — 10% of total

LAYER 2 — SUB-STAGES (Configurable per Job)

Each stage has 2–3 sub-stages. Increasable by admin for which structure shall be created.

Sub-stages are:

- Seeded from templates — Super Admin maintains a template library per job type (bathroom renovation, kitchen, full flat)

- Customisable per job — Coordinator, Admin, or Super Admin can add/remove/modify sub-stages for this specific job

- Proposable — Sub-coordinator or Supervisor can propose a new sub-stage or modification, which routes up for approval

Example — Stage 2 (M1) for Bathroom Renovation:

M1-A: Demolition complete — debris removed, base exposed

M1-B: Wall chasing complete — all pipe and conduit routes cut

M1-C: Concealed plumbing complete — CPVC pipes in walls, pressure tested

M1-D: Hydraulic pressure test passed — 10 bar held for 30 min

M1-E: Electrical conduit and wiring roughed in

M1-F: Waterproofing coat 1 applied — cured 24 hrs

M1-G: Waterproofing coat 2 applied — cured 24 hrs

M1-H: Pond test initiated — water filled, timer started

M1-I: Pond test passed — 24 hrs, no seepage confirmed

LAYER 3 — EACH STAGE  HAS FOUR DEFINED ELEMENTS

Element A — Description
Plain language name and scope of what must be completed.
Example: "M1-C: All CPVC pipes laid in wall chases, joints made, wall chases packed."

Element B — Duration
Planned working days. Entered during estimation. Tracked against actuals.
Example: "2 working days. Curing time: 0 days (no curing required for this sub-stage)."

Element C — Evidence Checklist
What the Supervisor must submit. Defined per sub-stage in the template. Specific to the sub-stage — not generic.

For M1-C (concealed plumbing):

- Photo of each pipe run before chases are packed

- Photo of all joints and connections

- Pressure gauge photo at 10 bar

- Timer start and end photo

- Confirmation that pipe route matches BOQ drawing

For M1-I (pond test pass):

- Photo of pond filled — water level marked on wall

- Photo of ceiling below — confirming dry

- 24-hour timer photo at start

- 24-hour timer photo at end

- Numeric entry: hours held

Element D — Checklist by Role

Each sub-stage has a role-specific checklist that is different from the evidence checklist. The evidence checklist is what is submitted. The role checklist is what each role must verify before passing or objecting.

| Role | What they check |
| --- | --- |
| Supervisor | Physical completion — is the work done as described? Evidence photos correct? Test results within spec? |
| Sub-Coordinator | Route compliance — does the work match the BOQ scope? Any deviation from plan? Material used as specified? |
| Coordinator | Commercial gate — is this sub-stage completeness sufficient to release payment? Any pending items that would affect next sub-stage? |
| Admin | Escalated exception only — when Coordinator cannot decide or flags a cost dispute |
| Super Admin | Policy exception only — when a scope change or deviation affects the overall contract value |

LAYER 4 — SUB-STAGE PROPOSAL AND APPROVAL FLOW

Who can propose a new STAGE or SUB-STAGE  or modify an existing one:

Supervisor → proposes → Sub-Coordinator reviews →

If approved: goes to Coordinator for final approval

If not sure: Sub-Coordinator forwards to Coordinator directly

Coordinator → approves or modifies → Done (for changes within job scope)

Coordinator → cannot decide → forwards to Admin

Admin → cannot decide → forwards to Super Admin

Super Admin → final authority

Rule: A sub-stage proposal cannot block ongoing work. Work continues on the current plan while the proposal routes through approval. Once approved, the sub-stage is added to the milestone schedule for future reference.

LAYER 5 — PAYMENT DECISION AT STAGE LEVEL

When a Stage is submitted for approval, the Coordinator makes one of five payment decisions. These are drawn from your specification above, with global practice (Procore's retainage model, UK defects liability framework) integrated:

Decision 1 — FULL RELEASE
All evidence items confirmed, tests passed, no defects observed.
100% of the sub-stage value released.
Condition: All checklist items confirmed, no outstanding items.

Decision 2 — PARTIAL RELEASE — RECTIFICATION PENDING
Work substantially complete but one or more minor items need correction. Correction does not require demolition or material replacement.
Coordinator specifies release % (suggested 70–90%) and lists items to rectify.
Balance held until rectification is confirmed and re-submitted.
Example: Tiling complete but 3 hollow tiles found — tiles to be replaced but rest of work is sound.

Decision 3 — PARTIAL RELEASE — REDO REQUIRED (SAME STAGE)
Work partially complete or partially defective. A portion must be redone but does not affect earlier sub-stages.
Coordinator specifies what must be redone, estimates time and cost impact.
Release % reflects only the confirmed-good portion (suggested 40–70%).
Example: Waterproofing coat 2 applied incorrectly on one wall — that wall must be redone, other walls confirmed good.

Decision 4 — HOLD — REWORK WITH MATERIAL LOSS
Work is defective in a way that requires demolition and fresh materials. Earlier sub-stage work may be affected.
No payment released until rework plan is submitted and approved.
Coordinator must specify:

- Which sub-stages are affected

- Estimated material cost of loss (deducted from contractor)

- Revised timeline

- Whether earlier payments need to be adjusted
Example: Waterproofing failed pond test — tiles already laid above must be removed, waterproofing redone, tiles relaid. Material loss is tiles plus adhesive.

Decision 5 — REJECT — COMPLETE REDO
Work is fundamentally wrong or fraudulent. Everything from this sub-stage must be demolished and restarted.
No payment for this sub-stage.
Previous sub-stage payments reviewed for adjustment.
Escalated automatically to Admin.
Example: Wrong pipe material used throughout — entire plumbing rough-in must be redone.

LAYER 6 — PAYMENT CALCULATION MATRIX

For each decision, the platform calculates:

Sub-stage value = (Stage % × total contract value) ÷ number of sub-stages in that stage

Decision 1: Release = 100% of sub-stage value

Decision 2: Release = coordinator-specified % of sub-stage value. Balance enters "held" pool.

Decision 3: Release = coordinator-specified % of sub-stage value. Redo items re-enter as a new mini-sub-stage.

Decision 4: Release = 0. Material loss estimate created as a deduction claim against contractor.

Decision 5: Release = 0. Sub-stage reset to pending. Admin notified.

Held pool: Any partial withheld amounts sit in a "retention pool" per job. Released when the specific rectification sub-stage is completed and approved. This prevents held money from being lost in the system.

LAYER 7 — DATABASE STRUCTURE NEEDED

Seven tables:

- milestone_stage_templates — Super Admin managed. One row per stage per job type. Stores stage name, code, default %, sequence.

- milestone_substage_templates — One row per sub-stage per stage template. Stores sub-stage name, code, description, planned duration, evidence checklist (ARRAY), role checklists (JSONB per role).

- job_milestone_stages — Per-job instance of stages. Cloned from template at estimation. Stores actual %, actual amounts, status.

- job_milestone_substages — Per-job instance of sub-stages. Cloned from template. Proposable and modifiable. Stores planned date, actual date, status, evidence submitted, payment decision, release amount, held amount.

- substage_proposals — Tracks new sub-stage proposals from Supervisor/Sub-Coordinator. Stores proposed by, current approver, approval chain status, proposed description and checklist.

- payment_decisions — One row per sub-stage payment decision. Stores decision type (1–5), release %, held amount, material loss estimate, rectification items, decided by, decided at.

- retention_pool — Per-job held amounts. Stores sub-stage reference, held amount, release condition, released at.

WHAT IS ADOPTED FROM GLOBAL PRACTICE:

From Procore: Ball-in-court routing (proposal goes to next level if current level cannot decide), workflow templates per job type, dynamic due dates per sub-stage, audit trail of every decision.

From UK JCT Contract / Defects Liability: Retention pool concept (held money with defined release conditions), partial completion certification, defects not blocking payment if non-critical.

From Australian AS4000 Standard: Practical completion at sub-stage level (work is complete enough to allow next trade to start even if minor items pending), separate defects list maintained alongside payment release.

From Indian Contract Act / Delhi HC precedent (confirmed in research): Milestone payment only releases when the defined trigger is achieved — substantial performance is not sufficient. Partial performance → partial payment only. This aligns exactly with your Decision 1–5 framework.

WHAT IS DIFFERENT FROM GLOBAL PLATFORMS (YOUR INNOVATION):

Global platforms (Procore, Buildertrend) do not have:

- Role-specific checklists per sub-stage (they have generic approval routing only)

- Material loss quantification built into the payment decision

- Automatic retention pool linked to specific rectification sub-stages

- Sub-stage proposal flow from field level up through approval chain

- Decision type taxonomy (complete waste / part waste / redo / rectify / material loss)